Magnet Digital Transformation Strategy (2025–2027)

Empowering inclusive, ethical, and youth-centered digital transformation

Created: March 2025

Last updated with Annexes: November 2025

SECTION 1. Where We Are Now

Magnet is a civil society organization working at the intersection of culture, youth work, education and social change. Through its rural base and international partnerships, Magnet develops participatory cultural and educational programmes that engage young people, artists, and local communities in processes of learning, co-creation, and social reflection.

Magnet House, our rural cultural and educational centre, functions as both a programme hub and a living laboratory for experimentation—hosting residencies, trainings, youth exchanges, and hybrid events that combine embodied, community-based work with digital participation.

Digital tools are already embedded in Magnet’s day-to-day operations, from organizing local and international activities to sustaining collaboration across borders. However, these practices have largely evolved organically rather than strategically. This strategy marks a deliberate step toward consolidating, reflecting on, and strengthening our digital practices so they align more clearly with our values, mission, and long-term vision.

Current Tools and Practices

- Communication: GoogleMeet and WhatsApp are widely used for meetings and informal coordination.

- Collaboration: Miro and other collaborative whiteboard tools and Google Drive are used across projects for brainstorming, facilitation, and documentation.

- Planning and Feedback: Notion and Padlet are occasionally used in specific activities, but without a standard usage model.

- Social Media & Outreach: Instagram and email newsletters are used to reach young people, though strategies vary by program.

Key Reflections from Internal Mapping (February 2025)

- Staff and volunteers frequently experiment with new digital tools and formats.

- There’s no unified approach to file storage, tool selection, or documentation.

- Data protection and youth safety are recognized as priorities, though implementation is still informal.

- While several projects include digital components, they are not yet consistently participatory or inclusive.

This foundation gives us both a clear starting point and a shared motivation to evolve not to digitize for its own sake, but to align our digital actions with our values and mission.

SECTION 2. Why Digital Transformation Matters

For Magnet, digital transformation is not a buzzword, it is a chance to live our values more fully in the digital world. Whether we are working with marginalized youth, building international solidarity or designing creative interventions, digital tools are now essential to how we operate and connect.

Why We Are Doing This

- To remove digital barriers that exclude youth from participating in civic and cultural life.

- To ensure resilience in our operations during times of disruption (e.g. pandemics, travel restrictions).

- To reflect our principles of equity, participation, and care in the tools and platforms we use.

- To enhance collaboration among staff, partners, and youth through clearer systems and shared knowledge.

Key Challenges

- Fragmented tool use and documentation lead to inefficiencies.

- Not all team members feel equally confident in navigating digital systems.

- Youth engagement often relies on consumption (watching, receiving), not creation (co-designing, leading).

- Data protection and safety protocols are inconsistently applied.

Guiding Values

- Inclusion: Every young person, regardless of ability, background, or connectivity, should have equal opportunities to participate.

- Transparency: Decisions about platforms, data, and workflows must be open, communicated clearly, and revisited collectively.

- Participation: Youth and staff should be able to influence how digital tools are chosen and used.

- Care: Well-being in digital spaces is a shared responsibility not an afterthought.

Magnet Digital Principles in Practice

Inclusion → Every digital activity must have a low-tech or offline alternative.

Participation → No digital campaign without youth involvement in concept or content.

Care → No recordings of youth without explicit, informed consent.

Transparency → Tools are chosen collectively and documented openly.

Digital transformation for Magnet means creating digital conditions that empower — not overwhelm — and cultivating environments where everyone feels safe, seen, and heard.

SECTION 3. Where We Want to Go

By 2027, we envision a Magnet where digital tools are not only functional but meaningful where digital practices reflect who we are and support the kind of youth work we believe in.

Our Vision

- All staff use shared digital tools with clarity and confidence.

- Youth actively co-create digital content and spaces, rather than just consuming them.

- Digital values are embedded in onboarding, training and project design.

- Resources are accessible across projects, languages and formats.

- Digital well-being, privacy, and care are treated as integral aspects of program quality.

Desired Shifts

| From… | To… |
| --- | --- |
| Ad-hoc tool use | Intentional, values-aligned digital systems |
| Staff-only decisions | Co-created practices with youth input |
| Digital as utility | Digital as participatory space for creativity and connection |
| Isolated digital skills | Peer-supported learning and shared capacity |

This transformation will not happen all at once but every small shift we make should move us closer to a digital culture that is open, inclusive and mission-driven.

SECTION 4. What We Will Focus On

We have identified four strategic focus areas where digital change can be both impactful and manageable. These pillars will shape our efforts through 2027.

A. Digital Tools and Infrastructure

Goal: Create a coherent, accessible and values-aligned ecosystem of tools across the organization.

- Audit current tools and eliminate redundancies.

- Establish an online office, with clearly marked folders with different levels of access,

- Establish onboarding materials and user guidelines for core platforms.

- Pilot alternative platforms (e.g. Nextcloud, open-source scheduling tools) to increase autonomy and privacy.

- Ensure hybrid tools are available and usable in every key activity.

Magnet Core Digital Stack (2025–2027)
By end of 2025, Magnet will operate with a clearly defined core digital stack:

- Internal communication:

  - WhatsApp → informal, urgent coordination only

  - Email → external & official communication

- Project collaboration & documentation:

  - Google Drive (structured folder system, shared across projects)

  - Notion → standardised for project tracking, onboarding and internal knowledge

- Facilitation & co-creation:

  - Miro (standard for workshops & youth co-design)

- Meetings & hybrid work:

  - GoogleMeet (with accessibility guidelines: captions, recordings when consented)

B. Data Ethics and Digital Safety

Goal: Integrate ethical standards, safety principles  and consent practices into all aspects of digital work.

- Develop a practical digital safety guide tailored to Magnet’s context.

- Map where and how data is stored and clarify responsibilities.

- Train staff in ethical use of digital tools and platforms.

- Introduce informed consent protocols in youth-focused programs.

C. Youth Participation and Communication

Goal: Shift from youth outreach to youth co-creation in digital spaces.

- Test new formats (e.g. digital storytelling labs, multilingual youth podcasts).

- Translate core communication content into youth-relevant languages.

- Design and pilot youth-led online campaigns or events annually.

- Ensure that every youth program includes at least one co-designed digital element.

D. Learning and Skills Development

Goal: Build internal capacity through reflective learning and peer-to-peer support.

- Launch “digital learning exchange” sessions, at least once a year. We also celebrate digital creativity and experimentation then.

- Set up a mentorship buddy system for new staff on digital practices.

- Collect and share good practices in a central resource hub (on GoogleDrive)

Not all tools or practices will be applied across all projects; relevance, scale and youth needs will guide proportional implementation.

SECTION 5. How We Will Take Action

Here are our first concrete steps toward implementation. These actions will be regularly reviewed and new steps added each year.

| Action | Who | When | Success Indicator |
| --- | --- | --- | --- |
| Conduct digital tools audit | Digital Focal Point | Q2 2025 | Tool map shared and validated |
| Draft digital safety guide | Ethics Lead | Q3 2025 | Guide reviewed by 100% of team |
| Host first digital learning exchange | All Staff | Q3 2025 | At least 10 participants, 80%+ satisfaction |
| Pilot youth co-creation digital campaign | Programme Team | Q2 2026 | Campaign reaches 500 youth |
| Conduct facilitated self-assessment on the inclusive elements of our digital space and practices | Ethics Lead | Q2 2026 | Digital Strategy includes assessment of the current state and practical guidelines relative to inclusion of young people in the digital space |
| Document good practices | Digital Working Group | Ongoing | Online resource hub updated quarterly |

Digital Roles at Magnet

- Digital Focal Point: Coordinates tools, documentation standards and learning exchanges

- Ethics & Care Lead: Ensures consent, safety and digital well-being principles are applied in programs.

- Programme Teams: Responsible for embedding at least one participatory digital element per project.

- Youth Digital Contributors (rotating): Young participants invited per project to co-design formats and give feedback.

Magnet House will function as a living laboratory for digital experimentation — blending rural space, embodied practices, and digital participation to test inclusive hybrid models.

Accountability will be maintained through check-ins at all-team meetings and working group updates. A mid-strategy review will be conducted in early 2026.

SECTION 6. How We Will Involve Others and Learn

Our digital transformation is a collective journey. Youth, staff and partners must be at the heart of it shaping not just how we use tools, but why and to what end.

Youth and Volunteer Involvement

- Youth-led advisory groups will test and review digital spaces and tools.

- Co-creation will be a requirement in all new digital campaigns.

- Feedback loops will be embedded in all pilot projects.

By 2026:

- At least 30% of digital content published by Magnet will be:

  - co-created with youth, or

  - youth-led with staff support

- Each flagship project will include:

  - one youth-designed digital output (podcast, zine, micro-site, reel series, etc.)

- Youth will be credited as co-authors or creators, not only participants.

Organizational Learning

- Quarterly reflection workshops will allow the team to assess progress and share experiences.

- Annual digital health check-ins will help track capacity and burnout risks.

- Feedback from youth and partners will be gathered through surveys, informal calls, and post-event evaluations.

Adaptation and Revision

- The strategy will be reviewed and updated in 2026 with input from all teams.

- Learnings will be openly documented and shared with our wider network.

- Flexibility will remain a guiding principle, our aim is not perfection but evolution.

Prepared by Magnet Team | March 2025

Based on the Digital Transformation and Governance Seminar (Feb 2025) facilitated in collaboration with IJGD as a part of the project “Digital Navigator: Empowering Youth Workers: Welcome to the Digital World” co-financed by the Erasmus+ Programme of the European Union.

This strategy is supported by practical annexes, including consent and participation statements, digital safety guidelines, ethical AI use guidance, and tool stewardship documents, which operationalise Magnet’s digital values in everyday practice.

Annex 1 → attach to applications / online forms

Annex 2 → internal handbook + facilitator briefings

Annex 3 → public-facing or semi-public

ANNEX 1: Digital Participation & Consent Statement (Magnet)

Who this is for:
All participants in Magnet’s seminars, trainings, residencies, exchanges, workshops, and online or hybrid activities.

### 1. Participation & Care

Magnet is committed to creating inclusive, respectful, and safe learning environments — both offline and online. By participating in this activity, you agree to engage respectfully with others and to follow the facilitation and safety guidelines shared by the Magnet team.

### 2. Digital Participation

Some activities may include:

- online meetings or hybrid formats

- collaborative digital tools (e.g. shared boards, documents)

- digital communication before, during, or after the activity

Participation in digital elements is voluntary, and alternative ways of engaging will be offered whenever possible.

### 3. Data & Privacy

Magnet collects only the data necessary to organise and deliver its programmes (e.g. name, contact details, participation-related information).
Your data will:

- be stored securely

- not be shared with third parties without your consent

- be used only for programme-related purposes

You may request access to, correction of, or deletion of your data at any time.

### 4. Photos, Video & Recordings

Magnet may document activities through photos, video, or audio for:

- reporting to partners and donors

- communication and visibility

- educational and archival purposes

You will always be informed in advance.
You may choose:

- ☐ I consent to being photographed / recorded

- ☐ I do not consent to being photographed / recorded

Consent can be withdrawn at any time without consequences.

### 5. AI & Digital Tools

If digital tools or AI-supported tools are used (e.g. for documentation, translation, or creative processes), this will be communicated transparently. AI tools will never replace participants’ voices, decisions, or authorship.

### 6. Questions or Concerns

If you have questions or feel uncomfortable at any point, you can contact:
Digital / Ethics Contact Person: Jelena Ristić
Email: jelena@magnet.house

☐ I have read and understood this statement and agree to participate under these conditions.

Annex 2: Digital Safety & Care Guidelines

These guidelines apply to all Magnet activities that include digital or hybrid elements.

### 1. Shared Responsibility

Digital safety and well-being are a shared responsibility between: facilitators, staff, volunteers, participants.

Care is not an afterthought — it is part of programme quality.

### 2. Safe Digital Spaces

Magnet commits to:

- using platforms appropriate to the age and context of participants

- moderating online spaces during activities

- preventing harassment, discrimination, or abusive behaviour

Disrespectful behaviour will be addressed immediately.

### 3. Youth Protection

For activities involving young people:

- clear facilitation roles will be defined

- private messaging between facilitators and minors is avoided or documented

- recordings are used only with explicit consent

### 4. Hybrid Events

For hybrid activities:

- online participants will be actively included, not treated as passive viewers

- facilitators will monitor both physical and digital spaces

- accessibility needs (connectivity, language, formats) will be considered

### 5. Reporting & Support

If a participant experiences discomfort, harassment or a safety issue:

- they can report it to a facilitator or the designated contact person

- concerns will be handled confidentially and with care

- Magnet will prioritise the well-being of affected participants

Annex 3: Ethical Use of AI & Digital Tools at Magnet

Magnet recognises the growing role of AI and digital automation and approaches these tools with curiosity, responsibility, and care.

### 1. Purpose of AI Use

AI tools may be used to:

- support drafting and editing of texts

- assist with translation or accessibility

- support creative experimentation

AI is used as support, not as a decision-maker.

### 2. What AI Will Not Be Used For

AI will not:

- replace human judgment in selection, evaluation, or decision-making

- replace youth voices, lived experience, or authorship

- be used to monitor or profile participants

### 3. Transparency & Authorship

- Use of AI-supported tools will be communicated when relevant

- Youth and participants will always be credited as creators or co-creators

- Final responsibility for content lies with Magnet staff and collaborators

### 4. Bias & Care

Magnet acknowledges that AI systems may reflect bias or exclusion.
Staff are encouraged to:

- critically review outputs

- avoid unreflective reliance on AI

- prioritise inclusive and context-aware approaches

### 5. Ongoing Learning

This guidance will be reviewed regularly as technologies and practices evolve.